## Read me
Fund, Fix or Stop: editable templates
Companion to the book. Copy and adapt these templates for use within your own organization.
Topic | Notes
How to use | Yellow cells are inputs. White cells with formulas calculate automatically. Each sheet has one example row from the book's fictional bank, Fytvio; replace it with your own data.
Status colors | Status is always written as text (Green, Amber, Red) so that it survives printing and color-blind viewing.
Defaults | Limits shown are the book's default starting points. Your signed threshold sheet sets the actual limits.
Self-assessment | Chapter 1. Ten questions and a score.
Inventory | Chapter 3. One row per use case: the twelve fields, the contract renewal date, and whether the investment is mandatory.
Explore entry | Chapter 13. One-page scoring of new ideas; eligibility and ranking are calculated.
Intake and tiering | Chapter 4. Six answers; the highest sets the tier.
Threshold sheet | Chapter 11. Limits, readings, and status by rule, including the trend rule with a minimum decline.
Five-test scorecard | Chapter 7. Overall status is the weakest test.
Value leakage | Chapter 9. Business case, four leaks, measured and realized value.
Monthly cost report | Chapter 10. Unit cost against plan with default Economics status.
Leadership page | Chapter 14. Spend by status from a list of investments.
Gate decision | Chapter 13. Record of a fund, fix once, or stop decision.
Red decision memo | Chapter 14. The five sections of the memo.
General tool value plan | Chapter 17. Role-based hypotheses and task-sampling results.
Vendor checklist | Appendix D. Due-diligence questions, what each answer decides, and the vendor's answers.
90-day tracker | Chapter 15. Activities, owners, and dates.
Example sheets | Three completed records from Appendix A, filled in for Fytvio: a threshold sheet, a Red decision memo, and a value confirmation with live formulas. They show the level of detail that lets a record stand as evidence.

## Self-assessment
AI portfolio self-assessment (Chapter 1)
Answer Yes only if you could show the evidence to an auditor this week. Partly counts as No.
# | Question | Yes / Partly / No
1 | Do you have one list of every AI system in use, including AI features in software you already own? | Partly
2 | Does every AI investment have a named business owner who is accountable for its results? | No
3 | Was a baseline measured before launch for your largest AI investments by spend? | No
4 | Is adoption measured as the share of eligible work done with AI, instead of licenses assigned? | No
5 | Is quality measured on live use, at least monthly, by people who did not build the system? | No
6 | Are serious errors counted separately, so a good average cannot hide them? | No
7 | Is cost tracked per transaction for each investment, as well as in total? | No
8 | Were Green, Amber, and Red limits agreed and signed before each investment went live? | No
9 | Is status confirmed by someone other than the team that runs the investment? | No
10 | Is value reported to leadership as realized only after Finance has confirmed it? | Yes
Yes answers
Reading

## Inventory
AI inventory (Chapter 3)
One row per use case. Low tier needs fields 1-7, 9, and 12.
Inventory no. | 1 Use case and purpose | 2 Business and technical owner | 3 Model, vendor, version | 4 Hosting channel | 5 Data classification | 6 Risk tier | 7 Approval date and conditions | 8 Threshold sheet link | 9 Monthly cost ($) | 10 Users and volume | 11 Value baseline and target | 12 Next review | 9 Contract renewal and notice date | Mandatory? Requirement it meets
FYT-014 | Answers customer questions on fees, payments, and card disputes | Head of customer services / customer platforms engineering lead | Mid-size hosted model, version pinned, vendor under a data processing agreement | AI gateway; vendor cloud, US region | Confidential customer financial data | High | Approved with conditions: AI disclosure to customers; kill switch; 150 sampled monthly | Threshold sheet v2 | 27000 | 420 agents plus customer chat; about 150,000 conversations a month | Baseline: 6 min 20 s handle time; target: 60-second reduction | Quarterly | Vendor contract renews each January; 90 days' notice | No

## Intake and tiering
Intake and risk tiering (Chapter 4)
Choose Low, Medium, or High for each factor. The highest answer sets the tier.
Factor | Low | Medium | High | Answer
1. What data does it use? | Public or internal | Confidential business data or staff personal data | Customer personal or financial data, regulated or partner data | High
2. Who sees or is affected by the output? | Internal team | Enterprise-wide or partners | Customers or the public | High
3. Does it inform, influence, or make decisions? | Informs a person | Influences operations | Credit, account, or financial outcomes | High
4. Can it act without a person approving? | Suggests to the user only | Drafts for others, with approval | Acts on its own | Medium
5. Which vendor and model? | Approved platform | Approved vendor, catalog model new to this use | New vendor, or model outside the catalog | Low
6. How many users, and what volume? | One team | Multiple departments | External or high volume | High
Tier (highest answer)
Number of High answers
Turnaround target (business days)
Item | Entry
Request name and inventory number | Complaint outcome letters to customers (FYT-031)
Business owner and technical owner | Head of complaints / correspondence platform lead
Decision and date | Approve with conditions
Conditions (each with owner and date) | Specialist approves every letter; outcome sentence from complaints system; 100 letters sampled monthly
Mandatory? If yes, the requirement it meets | No
Data readiness: available and owned; quality measured; use permitted | Complaint records available and owned by complaints team; quality checked; use permitted under existing terms
Layer: use case under a standard profile, or governed investment | Governed investment (High tier; output reaches customers)
Threshold sheet signed (governed investments) | Yes

## Explore entry
Explore entry scorecard (Chapter 13)
Score each idea Low, Medium, or High. Low strategic fit, no business owner, or data not ready means it does not enter. Mandatory investments skip the ranking. Check the record of stopped ideas first: a proposal with the same purpose must show what has changed since the stop.
Idea | Business owner | Business objective | Strategic fit | Size of value | Feasibility | Risk | Data ready? | Mandatory? | Eligibility | Rank score | Rank
Mortgage document checks | Head of mortgage operations | Faster mortgage decisions | High | High | Medium | Medium | Yes | No
Branch queue forecasting | Head of branch network | Lower branch staffing cost | Medium | High | High | Low | No | No
Suspicious activity report drafting | Head of financial crime | Meet reporting obligations | High | Low | Medium | High | Yes | Yes
Rank score is size of value plus feasibility (Low 1, Medium 2, High 3). Risk does not rule an idea out; it sets what Explore must prove.

## Threshold sheet
Threshold sheet and status rules (Chapter 11)
Direction: Higher if bigger is better, Lower if smaller is better. Red limit is the edge of the Red zone; leave it blank for leading signals, which set Amber at most. Leave readings blank if not collected.
Measure | Direction | Baseline | Green limit | Red limit | Min. sample | Min. decline | This period | Last period | Two periods ago | Sample size | Limit / data status | Trend | Type | Reason for the limits | Source and frequency
Live accuracy (%) | Higher | 92 | 90 | 86 | 150 | 2.5 | 91 | 92 | 93 | 150 |  |  | Performance limit | Green allows about two points of sampling variation below the 92% baseline; Red at the bottom of the sampling range for 150 samples | Reviewer-scored live sample, monthly
Critical errors reaching customers | Lower | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | Hard constraint | Customer-facing and High tier: any one is Red, no Amber band | Live sample, complaints, and grader flags, daily
Override rate (%), leading signal | Lower | 12 | 15 |  |  | 1 | 13 | 12 | 12 |  |  |  | Leading signal | Moves before accuracy does; sets Amber at most | Gateway, weekly owner check
Retrieval miss rate (%), leading signal | Lower | 4 | 6 |  |  | 1 | 4 | 4 | 4 |  |  |  | Leading signal | Moves before accuracy does; sets Amber at most | Gateway, weekly owner check
Unit cost per conversation ($) | Lower | 0.18 | 0.198 | 0.225 |  | 0.005 | 0.205 | 0.19 | 0.18 |  |  |  | Performance limit | Default limits: 10% and 25% above the $0.18 plan, not rounded | Cost metering, reconciled with the ledger monthly
Response time, 95% of answers within (s) | Lower | 3.1 | 4 | 6 |  | 0.2 | 3.3 | 3.2 | 3.1 |  |  |  | Performance limit | Set from the 3.1-second baseline | Gateway, daily
Overall status (lowest on the sheet)
A missing reading counts as missing data: report it as Amber. A critical event is Red the same day.
Sampled measures: a single reading below Green sets a watch and the next sample is doubled; a second low reading confirms Amber. A reading whose whole range sits below the Red limit is Red at once.

## Five-test scorecard
Five-test scorecard (Chapter 7)
Overall status is the weakest test. Use a dash for tests not scored at this stage.
Item | Entry
Investment, inventory number, and stage | Small-business lending agent (FYT-052), Pilot
Business owner | Head of business banking
Reporting period | Month 2
Test | Headline measure and limit | This period | Last period | Status | Cause (if Amber or Red)
Value | Rep time saved vs control; target 6 h/week | 5.5 h | 5.2 h | Green
Adoption | Share of eligible follow-ups; target 80% | 88% | 84% | Green
Trust | Live accuracy 92%; zero critical | 94%; 23 critical, one cause | 93%; 0 | Red | Outdated rate quotes sent to 23 businesses
Economics | Cost per email vs $0.10 plan | $0.09 | $0.09 | Green
Delivery | Milestone slip 2 weeks or less | On schedule | On schedule | Green
Overall | Weakest test

## Value leakage
Value measurement and leakage (Chapter 9)
Annual figures in dollars. Leaks are entered as positive amounts.
Line | Annual value ($) | Cause | Owner
Business case (net benefit) | 10000000 | Net of planned running cost | Business owner
Adoption gap | 2400000 | Two lines of business not connected; handwritten forms routed around | Business owner
Process not redesigned | 1500000 | Full field check kept | Operations
Quality rework | 900000 | Handwritten form extraction errors | Delivery team
Cost overrun | 700000 | Largest model used for every document | Delivery team
Measured net benefit
Measured as share of business case
Full running cost (planned plus overrun) | 1700000
Classification of gross benefit | Annual value ($) | Evidence
Harvested | 2400000 | 20 vacant positions not refilled
Redeployed | 1200000 | Loan-processing backlog reduced by a measured amount
Unharvested | 2600000 | Capacity created, not yet used for named work
Realized gross (harvested plus redeployed, Finance-confirmed)
Realized net (gross less full running cost)
Realized net as share of business case
Value test on realized net (default limits)
Check: classes add up to gross benefit

## Monthly cost report
Monthly cost report (Chapter 10)
One use case per copy of this sheet. Dollars per month.
Item | Plan | Actual | Variance
Completed transactions | 150000 | 200000
Model usage ($) | 10500 | 19000
Share of platform cost ($) | 7500 | 10000
Licenses ($) | 3000 | 4000
Support effort ($) | 6000 | 8000
Total cost ($)
Unit cost ($ per transaction)
Economics status (default limits)
Forecast variance over 15%?

## Leadership page
Monthly leadership page (Chapter 14)
List every investment with its annual spend and overall status.
Investment and stage | Annual spend ($) | Overall | Tests not Green | Decision or help needed
Customer service assistant (Run) | 400000 | Amber | Economics | Fix: unit cost 14% over plan
Document intake (Scale) | 1700000 | Red | Value; Adoption; Economics; Delivery | Fix: leakage review; 19% realized net
Fraud model (Run) | 900000 | Amber | Trust | Fix: precision down two months
Coding assistant (Run) | 1200000 | Green
Total spend ($)
Share of spend in Green
Share of spend in Amber
Share of spend in Red
Red spend target (10% or less) met?

## Gate decision
Gate decision record (Chapter 13)
Item | Entry
Investment, inventory number, and tier | Contract review (FYT-077), Medium
Gate | Explore to Pilot
Criteria agreed at the start of the stage (date) | 90% on 300-clause test set; baseline captured
Evidence against each Green criterion | 92% on second iteration; baseline 3.5 hours per contract
Evidence against each stop criterion | Target met; stop criterion not triggered
Five-test status at the gate | Trust Green (test set); Delivery Green
Decision | Fund
If fix: actions, owner, and end date
If fund: next-stage budget cap, end date, Green and stop criteria | $250,000; four months; review time 30% lower than control
If stop: retirement steps, budget returned, lessons recorded
Decided by, date, and dissent | Governance lead and sponsor

## Red decision memo
Red decision memo (Chapter 14)
One to two pages. Circulate before the review board meeting.
Item | Entry
Investment, stage, and inventory number | Chat tools, three (Run)
Cause and evidence | Three tools doing the same job; 2,300 licenses, about 900 weekly users; no baseline
Options (fix: cost and timing; stop: write-off and money released) | A keep all; B consolidate to one tool (about $450,000 a year); C stop all
Customer impact, and risk impact | Option B moves all use under the strongest data terms
Recommendation | Option B, migration within 90 days
Decision needed by | Next review board meeting
Decision, date, and dissent (after the meeting)

## General tool value plan
General-purpose tool value plan (Chapter 17)
One row per role group. Times are minutes per task from task sampling or the cohort comparison.
Role group | Named task | Minutes without | Minutes with | Change | Measurable? | Decision
Credit analysts | Credit memo on a loan application | 35 | 26 |  | Yes | License
Finance analysts | Monthly variance commentary | 90 | 72 |  | Yes | License
Service supervisors | Call quality notes | 20 | 17 |  | Yes, smaller | License
HR advisers | Replies to policy questions | 12 | 11 |  | No | Request pool only
Seats |  | 950
Price per seat per month ($) |  | 30
Annual cost ($)
Note on C18: Illustrative price from the book. Use your contracted price.

## Vendor checklist
Vendor due-diligence questions (Appendix D)
Not legal advice. Review answers with Procurement and Legal.
Area | Question | What the answer decides | Vendor answer | Acceptable?
Data use | Is our data used to train or improve your models? Can that be excluded in the contract? | Which data classes the platform may receive
Retention | How long are prompts, outputs, and logs kept, and can we set the period? | The data classes allowed and the contract retention clause
Location | Where is our data processed and stored, and which subprocessors are involved? | Whether data residency rules are met
Security | Which independent security assessments can you share? | Whether the security review can rely on them or must test itself
Regulated data | Will you sign the data protection terms our regulators require for customer data? | Whether customer data may be used at all
Model changes | How much notice before a model version changes or is retired? Can we test first? | The fallback plan and the budget for re-testing
Evidence | Can we run our own test set before signing? | Whether the Trust test can be scored before purchase
Reporting | Can usage and cost be reported by our use case or department? | How cost is allocated on the threshold sheet
Incidents | How quickly will you notify us of a security or quality incident? | Whether the incident process can meet its own deadlines
New features | Can new AI features be kept off until we enable them? | Whether new features can wait for intake
Continuity | What happens to our service if your model is withdrawn, your service fails, or your company leaves the market? | The manual fallback and the exit budget
Exit | Can we export our data, prompts, and configurations if we leave? | How much lock-in the portfolio review must price in
Answers marked No or Needs follow-up

## 90-day tracker
90-day plan tracker (Chapter 15)
Days | Activity | Owner | Done
1-14 | Governance lead confirmed; review board charter approved
1-30 | Inventory built from invoices, contracts, expenses, sign-on records, scans
1-30 | Spend baseline set; owner assigned to every entry
1-30 | Current review processes mapped
21-30 | Top 20 investments by spend agreed
31-45 | Intake and tiering launched in the existing intake form
31-60 | Gateway logging, tagging, and identifier checks switched on
31-45 | Model catalog and measure definitions published
31-60 | Threshold sheets signed for the top 20
31-60 | Data sources connected for monthly status
61-80 | First test sets and live samples for High-tier systems
61-90 | Weekly owner checks started
75-85 | Status rules applied; first monthly health report issued
85-90 | First portfolio review; fund, fix, and stop decisions recorded
Activities done

## Example threshold sheet
Completed threshold sheet: customer service assistant (Chapter 11)
Completed example from Appendix A, for the fictional bank Fytvio. Use it as a guide to the level of detail; record your own in the blank template.
Item | Entry
Use case | Customer service assistant. High tier. Run stage.
Signatures | Business owner (head of customer services) and AI governance lead, signed and dated. Review board approval recorded in its minutes.
Version | Version 2. Re-approved after the test set was rebuilt (Chapter 8). Version 1 kept on file.
Exceptions in force | None.
Critical errors reaching customers | Hard constraint. Any one is Red, with no Amber band. Reason: the assistant is customer-facing and High tier. Source: live sample, complaints and grader flags, checked daily.
Live accuracy | Performance limit. Green 90% or higher, Red below 86%. Reason: Green allows about two points of sampling variation below the 92% baseline; Red sits at the bottom of the sampling range for 150 samples. Minimum sample 150 a month; minimum decline 2.5 points. Source: reviewer-scored live sample, monthly.
Test-set accuracy | Performance limit. Green 92% or higher, Red below 89%. Reason: set from the 94% baseline on 400 cases. Source: evaluation service, on every change and monthly.
Share of eligible questions handled | Performance limit. Green 70% or higher, Red below 52.5%. Reason: default limits, 75% of the 70% target for Red, not rounded. Source: contact center system, monthly.
Unit cost per conversation | Performance limit. Green $0.198 or lower, Red above $0.225. Reason: default limits, 10% and 25% above the $0.18 plan. Source: cost metering, reconciled with the ledger monthly.
Response time | Performance limit. 95% of answers within 4 seconds is Green; above 6 seconds is Red. Reason: set from the 3.1-second baseline. Source: gateway, daily.
Handle-time reduction | Performance limit. Green 54 seconds or more, Red below 42 seconds. Reason: set from the 60-second target. Source: contact center system against the baseline; turned into realized value by Finance each quarter.
Override rate and retrieval miss rate | Leading signals. Above 15% and above 6% set Amber at most. Reason: they move before accuracy does. Source: gateway, weekly owner check.

## Example Red memo
Completed Red decision memo: small-business lending agent (Chapter 14)
Completed example from Appendix A, for the fictional bank Fytvio. Use it as a guide to the level of detail; record your own in the blank template.
Section | Content
Investment | Small-business lending agent (FYT-052). Pilot stage, month 2. Level 2: a relationship manager approves each email.
Cause and evidence | The agent took rates from a document library that still held last quarter's rate sheet. The monthly live sample found one wrong quote; gateway logs found all 23 within two hours. Quotes were 0.25 to 0.5 percentage points too low. Approvals missed them because emails were approved in batches, some 30 or more in a few minutes.
Status | Red the same day under the critical event rule. Agent paused. Other tests Green: value 92% of target, adoption 88%, cost below plan.
Option 1: fix once | Take rates from the pricing system, add 40 test cases, limit batch approval to ten emails and open every email with a price. Cost: team time and two more months of pilot running cost. Timing: two months to show the fix holds.
Option 2: stop | Write off pilot spend to date and return the remaining pilot budget to the portfolio pool. The time saving of about 5.5 hours a week per manager is lost.
Customer and risk impact | 23 businesses received wrong quotes; each was called with a corrected quote. Handled as a Sev 1 incident. Compliance is reviewing fair lending and state-law exposure.
Recommendation | Fix once. The cause is specific and testable, and the fix removes the model from writing rates.
Decision needed by | Ten business days from the Red status.
Decision and dissent | Fix once, as recommended, with two months to show it holds. Dissent recorded: one member asked for a stop, on the grounds that Level 2 approval had failed and might fail again.

## Example value confirmation
Completed value confirmation: document intake (Chapter 9)
Completed example from Appendix A, for the fictional bank Fytvio. Yellow cells are inputs; the rest calculate, so the example can be reused with your own figures.
Line | Value | Evidence or note
Baseline minutes per document | 6 | Measured for six weeks before launch
Planned minutes per document | 2 | Business case
Documents per year | 2500000 | Baseline period, annualized
Loaded cost per hour ($) | 66 | Agreed with Finance in advance
Planned running cost per year ($) | 1000000 | Business case
Business case gross benefit ($) |  | Minutes saved, in hours, times the loaded cost
Business case net benefit ($)
Leak (annual, entered as positive) | Value | Cause
Adoption gap | 2400000 | 78% of eligible documents went through the system
Process not redesigned | 1500000 | Full field check kept
Quality rework | 900000 | Handwritten form extraction errors
Cost overrun | 700000 | Largest model used for every document
Measured net benefit ($) |  | First Finance review, two quarters into Scale
Classification | Value | Evidence
Harvested | 2400000 | 20 vacant intake positions not refilled, visible in the budget
Redeployed | 1200000 | Clerks moved to the loan-processing backlog, which fell by a measured amount
Unharvested | 2600000 | Capacity created, not yet used for named work; reported as capacity, not money
Realized gross ($) |  | Harvested plus redeployed, confirmed by Finance at quarter-end
Full running cost ($) |  | Planned cost plus the overrun
Realized net benefit ($) |  | Compared with the net business case
Gross measured benefit ($) |  | Net benefit plus full running cost
Check: classes add up to gross benefit |  | The classes split gross benefit, before running cost
Value-to-cost ratio |  | Floor 1.5 at Scale and Run; Red below 1.0
Measured net as share of business case |  | Sets status at the Scale stage
Realized net as share of business case |  | Sets status from the Run stage
Value test (default limits) |  | On measured value at Scale. Green at 90% or more of the business case; Amber 70 to 89%; Red below 70%
Next confirmation | Next quarter-end, after the four fixes in Chapter 9